## Sheet1
Study Abroad Management System (SAMS)
Risk | Risk Resolution Measures | Justification
Under Estimated Schedule | Additional 2 weeks added into schedule. | The additional time added into the schedule should provide sufficient time to resolve any minor delays.
Frequent Requirement Changes | Inclusion of End User and development team throughout project. | Including the stakeholders of the project should allow for a decreased effect of any requirement changes.
Operational Scheduling Conflicts | Development team solely assigned to SAMS project. | The development team is to be scheduled only for the current project to allow their focus to remain on their assignments.
Incorrect User Interface Design | Prototyping and End User Involvement | Prototyping will allow the end user to provide feedback to determine if the UI meets their needs.
Incorrect Function Development | Organization Analysis and Prototyping | Organizational analysis allow the the development team to provide more effective functions. Prototyping will allow end user to provide benefical feedback.